## DTT Test Hour Log
Instruction: Fill in the number of hours that you worked on the test. Breakdown into sub-tasks and include descriptions where possible to get a better overview of the process.
Subject | Date | Amount of hours | Description
Start of project + Git | 2017-12-04 | 0.25 | I made a blank new project in Xcode and added a gitrepository to it
Implementing assets + first setup mainviewcontrollor | 2017-12-04 | 1 | Implemented all the assets to the project. First viewcontroller visual setup. Added the constrains.
Research navigationcontroller/bar | 2017-12-08 | 0.5 | I made the dessision of implenting a navigationbar instead of an image
Implementation of the about view | 2017-12-08 | 1 | Displaying an image and a textfield with a url that rederects to the site
Implementation of the mapview | 2017-12-08 | 0.5 | Setting up the basics of the mapview
Displaying your location on a popup | 2017-12-11 | 6 | Getting the userlocation and converting the longitude/latitude to an adress.
Implementation of the callbutton | 2017-12-11 | 1 | Setting up the callbutton and displaying another view for calling the phonenumber
Added the call function | 2017-12-11 | 0.5 | Creating a function that allows the user to call the phonenumber that was given.
Making the code structure clear. Adding missing comments | 2017-12-11 | 0.25 | Making the code readable for everyone.
Added the Scrollview | 2017-12-20 | 1 | Implenting the scrollview in the about section
Research Traits | 2017-12-20 | 0.50 | I didnt know what this was. So i started to learn how it worked.
Traits for the aboutview | 2017-12-20 | 1.50 | Traits for every device for the aboutview
Traits for the homeview | 2017-12-20 | 1.50 | Traits for every device for the homeviewcontroller
Traits for the mapview | 2017-12-21 | 1.50 | Traits for every device for the mapviewcontroller
Appstructure | 2017-12-21 | 0.50 | The mapstructure of the app is now better
GPS permissions | 2017-12-21 | 2 | Asking with alertviews for permission of the gps
Traits failures | 2017-12-21 | 2 | The traits didnt worked that well. I needed to set them again for several times.
Internet connection | 2017-12-21 | 0.5 | I searched and tried to understand what i needed to do. But i didnt know where i needed to check.
App icon + Rotate | 2018-01-02 | 0.25 | I improved the app icon. Now it hasn't a black border anymore. And a solved the rotating issue.
Total amount of hours | 14.5